## Slide 1: Memorandum of Understanding between Police, CPS and NHS Project Management Llandrindod Wells, 9 June 2017
By
Andrew Hynes
Legal and Risk Services

## Slide 2: Background
An MOU has been in existence between the three parties for over ten years.
The agreement followed a similar agreement made between these parties in England.
The agreement was reviewed and amended as part of a wider approach to the problem of violence against NHS staff considered by the NHS Wales V&A Steering Group sponsored by the then Minister for Health, Edwina Hart and shared by Sheila Lloyd and latterly chaired by David Francis the Chairman of the Cardiff and Vale University Health Board.
The MOU was revised approximately 3 years ago but only minor revisions were applied.
It is acknowledged that the MOU is overdue for an overhaul and in re-launch.
The MOU is universally considered to be a success, that notwithstanding it requires a root and branch review and a reinvigoration of public police, NHS and CPS awareness

## Slide 3: Project Definition - Objectives
1. Review MOU to reflect changes since original inception, these being inter alia:-
Changes in prevalence, tight in nature of the offences against NHS staff.
Changes in applicable laws, to reflect changes in case law and criminal legislation
Changes in procedure/policy within CPS police and NHS in dealing with violent crime.
Changes in information governance control.
Changes in government policy in relation to violence and aggression against NHS staff.
Changes in sentencing guidelines for such offences.
Changes in operational structures and individual staffing (staff turnover).
2. Effect and negotiate changes to reflect requirements of three parties
3. Re-launch of MOU
To increase public awareness
To increase police awareness
To increase NHS awareness
To increase CPS awareness
Reinvigorate collaboration between the three parties by a series of National workshops.
Design and implement training and educational workshops
Coordinate a press release on a national basis for attempt to foster international recognition of the initiative for Welsh Government method: –
Project management approach will be bespoke following principles of Prince 2.

## Slide 4: Scope
Limited to objectives but with a view to extending the debate into encompassing an approach to non intentional violence within NHS Wales i.e. adoption of Calming the Storm or similar initiative. (Exclusions theft and criminal damage)

## Slide 5: Deliverables
A comprehensively reviewed, revised and publicised memorandum of understanding which will increase appropriate prosecutions against the perpetrators of violence upon NHS staff.

## Slide 6: Desired outcomes
A revised MOU will assist in deterring violent conduct against NHS staff and provide public and NHS assurance that a zero tolerance policy is being adopted.

## Slide 7: Constraints
There will only ever be a finite hopefully reducing the number of violent incidents against NHS staff. Interfaces
Consideration needs to be given to that other initiatives within NHS Wales and within the police force and CPS that may be encountered.

## Slide 8: Assumptions
The key assumption in this is that the three parties see the utility and have a common goal in attempting to more effectively deal with the prosecution of appropriate offenders in this area of concern.

## Slide 9: Project Organisation Structure
Sponsor – Andrew Goodall, Cabinet secretary's office
Project Board Steering Team
Project Manager, Project Team and their roles and levels of responsibility to be agreed.

## Slide 10: Communications Plan
Appended to it the SPT management checklist

## Slide 11: Potential Project Risks
Potential Risks | How will we manage the risk
1. Competing demands | 
2. Inadequate resources | 
3. Project drift | 

## Slide 12: Resource requirements
Required resources will be participant, time, training materials, miscellaneous expenses

## Slide 13: Timescales
Start and finish charts
NB – Gantt chart should be used to plot project timeline – outstanding

## Slide 14
Ql. Response | What is your own personal perception of the effectiveness of the Memorandum of Understanding? I can only comment on my area North Wales for all the questions - in my opinion MOU is not as effective as hoped for | the
Q2. Response | What are the successful aspects of the MOU? SPOCs were established when the MOU was first introduced | 
Q3. Response | Do you have any specific problems that the MOU fails to address? No particular problems but perhaps it could recognise the different challenges the ambulance service face compared to hospitals etc | 
Q4. Response | How well known in your view is the existence of the MOU; Within the Police? -Not well known Within the NHS? -Ambulance Service- Fairly well Within the CPS?- Cannot comment in this area as I have not had a lot of experience of dealing with CPS | 
MEMORANDUM OF UNDERSTANDING BETWEEN POLlCE, CPS AND NHS QUESTIONNAIRE FOR CASE MANAGERS, POLICE REPRESENTATIVES AND NHS REPRESENTATIVES
N.B Before completing this questionnaire it is suggested that you consider the current version of the MOU before you make your comments.

## Slide 15
Q5. Response | Is the Case Managers role as described within the MOU an accurate reflection of what Case Manager actually does? Not exactly in my situation, in a Jot of cases first line managers (as they have always done) carry out the duties with my support if required | the ys S
Q6. Response | Are the arrangements for the sharing of information between the CPS, Police and NH satisfactory? Not in my experience | 
Q7. Response | Are the arrangements to review the ongoing work of the MOU working effectively? Unsure | 
Q8. Response | Could you estimate the number of meetings you have had with the CPS/NHS/Police to discuss aspects of the MOU since its inception? One | 
Q9. Response | Please provide examples of specific cases which demonstrate:- 1. Where your relationships with the Police are good; Initial meeting 4 years ago with Police SPOCs 2. Where you demonstrate your relationship with the CPS is good; N/A 3. That you demonstrate your relationship with the NHS is good. ' Regular sharing of information with BCUHB Case Manager | 

## Slide 16
Q10. Response | Could you please confirm the Police SPOC for the MOU in your area. Do not know current SPOC
Q11. Response | Could you please confirm who the CPS SPOC is for your Heal$ Board. As above
Q12. Response | Who is the Executive lead for your Health Board in relation to violence and aggression Claire Bevan -Executive Director Quality, Safety & Patient Experience James Mycroft will be the Non-Executive Lead for Risk, H&S and V&A
Q13. Response | Is that person aware of the existence of the MOU. Yes
Q14. Response | What is The Role of A Case Manager. In my situation to ensure support is provided and assist where necessary
Q15. Response | Is there a difference between gratuitous and non gratuitous violence in the way that you provide assistance following a violent attack. No
Q16. Response | Finally are there any additional matters that you would like dealt with within the MOU Confirmation and maintenance of SPOCs established at a higher level Specific training/qualification to a recognised standard/level for case managers Standardisation of documentation used for record keeping

## Slide 17
Stage | Details | Dates | Completed
1. Project initiation agreed |  |  | 
2 End product operationally defined |  |  | 
3. Project Manager appointed |  |  | 
4. Project resources specified and agreed |  |  | 
5. Project team established |  |  | 
6. Start date agreed |  |  | 
7. Date by which product will be delivered agreed |  |  | 
8. Milestones and dates to be achieved specified |  |  | 
9. Dates for project meetings agreed |  |  | 
SPT: Project Management Checklist

## Slide 18: Article South Wales Argus Jan 17
FIVE NHS staff a day in Gwent were physically or verbally attacked during 2015/16, according to new figures.
There were 872 incidents of what Aneurin Bevan University Health Board describes as ‘physical abuse, assault or violence’ in the year to March 31.
And in the same 12-month period, staff reported 949 incidents of verbal abuse or disruption.
Last year’s figure for physical attacks was down from 1,067 in 2014/15, but nevertheless contributed to a catalogue of violence against NHS staff in Wales that approached 4,000 incidents.
And last year’s 949 verbal abuse or disruption incidents in Gwent was almost 45 per cent up on that for 2014/15.
Over the past five years in Gwent there has been a total of 7,501physical or verbal attacks on staff.
A health board spokesman said the increase in reported verbal abuse is likely a result of staff being encouraged to report incidents.
Taken together however, abuse of NHS staff in Gwent has risen steadily, with overall reported incidents up almost 50 per cent in five years.
“The health board has seen an increase in figures of verbal assaults over the past five years,” said a spokeswoman.
“This rise is due to an increase in staff reporting incidents following training we have provided to raise awareness of the issue.
“Previously, staff members were reluctant to report verbal assault but the health board actively encourages staff to report verbal assault cases.
“With regard to physical assaults, the health board works closely with the police to ensure safety for our staff.
“In addition, we have an ongoing marketing campaign to educate the public that abuse to staff is not acceptable.”
Wales-wide, a mixed picture of abuse toward NHS staff emerges, some health boards reporting increases in physical abuse and/or verbal abuse in the past year, and others reporting decreases. But in all cases, the figures are unacceptably high.