Morriston Infrastructure Phase 2 Stage 2

​​ ​[image: image1.jpg]$5>

¥

/
0

g_
&20

=
>
-
m
A

Bwrdd lechyd Prifysgol
Bae Abertawe

Swansea Bay University
Health Board





[image: image2.png]Photos - electrician-team-work-electrical-panel-tiny-people-cartoon-characters-concept-vector-illustration-electrician-team-work-186886699,pg

—+ Addto

3R Edit & Create

- - T Q)

Appointment £ L
= L] i 7
2] Scheduling Assistant

Cancel Join Teams Meeting ~ Meeting
X Tracking ~

Meeting Meeting Options ~ Notes.
Adtions Show Teams Meeting  Meeting Notes

@ Attendee responses: 1 accepted, 0 tentatively accepted, 0 declined.

%]

Contact

£
Ye

Attendees -

Attendees

- ?Recurrence > o
Time Zones
= Tags  Meeting  Viva New

RoomFinder ' - Notes Insights Meeting Poll Templates
Options OneNote FindTime My Templates

To. ¥ Christine Morrell (Swansea Bay UHB - Therapies And Health Sciences

Subject | Catch up - Pathology & PET CT

Location | Microsoft Teams Meeting

Starttime | Thu 10/03/2022

Endtime | Thu10/03/2022

[] All day event

FrvieroooTe 1

Join on your computer or mobile app
Click here to join the meeting

Join with a video conferencing device

Video Conference ID: 123 662 303 0
Alternate VTC instructions

In Shared Folder [E] Calendar

Last modified by Heather Edwards (Swansea Bay UHB - Capital Planning) on Wed 20:44

rvice Desk
jal - 44400
hal - 01639 684400

C7LAPJGVZMF2

sion
t Explorer

C7SRVDOMO0001
YMRU
Unite

14:55
10/03/2022




v.final

Document control sheet

	Client
	Swansea Bay University Health Board (SB UHB)

	Document Title
	Morriston Infrastructure Phase 2 Stage 2

	Version 
	final

	Status
	final

	Author
	Heather Edwards

	Date
	5th July 2022

	Further copies from
	email: heather.edwards2@wales.nhs.uk quoting reference and author


	Contact details

	Main point of contact
	Telephone number
	Email address
	Postal address

	Heather Edwards
	01792 286119
	heather.edwards2@wales.nhs.uk 
	


Contents

61
The Strategic Case


61.1
Introduction


61.2
Background


7Part A - The Strategic Context


71.3
Business Strategies


71.4
Key Interdependent Projects


8Part B - The Case for Change


81.5
Problems with Status Quo


81.6
Spend Objectives


81.7
Business Needs


81.8
Potential Scope


91.9
Main Outcomes and Benefits


91.10
Main Risks


101.11
Constraints and Dependencies


112
The Economic Case


112.1
Introduction


112.2
Critical Success Factors


112.3
Methodology


112.4
The Long Listed Framework Options


122.5
Summary of Short List Options


122.6
Indicative Capital and Revenue Costs of each Short Listed Option


132.7
The Preferred Option


153
The Commercial Case


153.1
Introduction


153.2
Required Services


153.3
Key Appointments & Contract Arrangements


153.4
Required Facilities and Compliance


153.5
Potential for Risk Management


153.6
Agreed Charging Mechanisms


153.7
Agreed Contact Length


153.8
Personnel Implications (including TUPE)


153.9
FRS5 - Accountancy Treatment


163.10
Indicative Timescales


174
Funding and Affordability


174.1
Introduction


174.2
Capital


184.3
Impact on the Balance Sheet and Impairment


184.4
Income and Expenditure Analysis


184.5
Overall Affordability


195
The Management Case


195.1
Introduction


195.2
Project Management Arrangements


205.3
Project Bank Account


205.4
Use of Special Advisers


205.5
Arrangements for Benefits Realisation


205.6
Building Design Strategy and Decarbonisation


205.7
Community Benefits


205.8
Audit & Assurance


215.9
AEDET (Achieving Excellence Design Evaluation Toolkit) & BREEAM


215.10
Arrangements for Risk Management


215.11
Planning Permissions


215.12
Post Evaluation Arrangements / Lessons Learned


215.13
NHS Wales Gateway Review (Stage 3 – Investment Decision)


215.14
Contingency Plans




Figures 

7Figure 1 – Interdependent Projects


8Figure 2 – Spend Objectives


9Figure 3 - Potential Service Scope Framework Options


11Figure 4 – Critical Success Factors (CSFs)


12Figure 5 – Short List Options


12Figure 6 – Capital Costs (excl recoverable VAT £000s and including Optimism Bias above baseline)


13Figure 7 – Revenue cost impact above baseline (£000’s)


16Figure 8 – Key indicative milestones


17Figure 9 – Capital Costs (incl recoverable VAT £000s and Optimism Bias above baseline)


18Figure 10 – Capital Expenditure £000’s (incl of non-recoverable VAT & excl Optimism Bias)


18Figure 11 – Revenue Expenditure £000’s above baseline (£000s)


18Figure 12 – Revenue cost impact above baseline (£000’s)


19Figure 13 – Environment Modernisation Programme Management Structure


20Figure 14 – Morriston Hospital’s Project Management Structure


20Figure 15 – Special Advisors




Appendices 
22Appendix A – Risk Register


23Appendix B – Project Board Membership


24Appendix C – Framework Option Appraisal


25Appendix D – Cost Form


26Appendix E – Optimism Bias Mitigation


27Appendix F – Whole Life Costing


28Appendix G – Drawings


29Appendix H – Management Control Plan


30Appendix I – Terms of Reference


31Appendix J – Benefits Realisation Plan


32Appendix K – Benefits Realisation Register


33Appendix L - Audit & Assurance Plan


34Appendix M – Gateway Review - (RPA)


35Appendix O – VAT Letter


36Abbreviations


1 
The Strategic Case 
1.1 Introduction 
This Business Justification Case (BJC) seeks support from Welsh Government (WGov) of £16.533m (including recoverable VAT and excl Optimism Bias) for strategic capital investment to address significant electrical infrastructure condition, capacity risks and compliance issues, and to provide compliant ventilation infrastructure in the Hospital Sterilisation and Decontamination (HSDU) Dept. at Swansea Bay University Health Board’s (SBUHB’s) Morriston Hospital, Swansea.
The risk rating on Morriston Hospital’s existing sub stations is ranked a significant risk. Our status quo issues are non-compliance, overloading risk to existing generators, and electrical protection issues will not be resolved. Neither Substation 3 or 4 is compliant with current British Standards or WHTM requirements and both are at risk of overloading their LV electrical supply with potentially serious consequences for clinical services, clinical delivery and patient safety - if Substation 3 or 4 were to fail it would disrupt Morriston’s theatres and theatres recovery areas and Radiology services. This investment is therefore a key priority for Health Board plant & systems.
Current ventilation system at Morriston’s HSDU is also a high risk as regards non-compliance with ventilation rates - only 50% of required standards and pressure cascade non-compliant. Enhanced environmental air monitoring has been put in place to provide some assurance but this has also been failing recently requiring continual re-testing. This investment will address these issues and provide compliant infrastructure.

1.2 Background
This case is part of a programme for investment as outlined in SBUHB’s Programme Business Case (PBC) (previously Strategic Outline Business Case (SOC)), which outlined an overall investment of approx. £60m and was approved by Welsh Government on the 22nd April 2016. The PBC identified key programme drivers, addressed the need for high standards of ward environment and compliant supporting infrastructure, and supported national and local strategy and good practice documents, including Designed for Life: Creating World Class Health and Social Care for Wales in the 21st Century (WG) and Together for Health (WG).

The need for safe and reliable estate infrastructure remains a top priority area for SBUHB and supporting clinical services is the corner-stone of our strategic plan. Significant failures in essential infrastructure systems and essential plant have highlighted the importance of maintaining safe and efficient service delivery, uninterrupted patient care, system resilience, and infrastructure and electrical capacity to support clinical services. 
In supporting WGov’s Decarbonisation Strategy we aim to deliver additional electrical capacity and optimise links with SBUHBs wider renewable energy infrastructure solutions, i.e. the new Solar Farm.
To date, the Health Board has progressed two major infrastructure investments: 

· Environmental Modernisation BJC Stage 1 (BJC1) was approved by Welsh Government on the 5th January 2017. This delivered a number of environmental and estates infrastructure investments valued at £7.768m (incl vat) at Morriston, Singleton and the Prince of Wales Hospitals, prior to Health Board boundary changes. Works were completed in 2017/18. 

· Environmental Modernisation BJC Stage 2 (Phase 1) was approved by Welsh Government on the 13th December 2018. This delivered environmental and estates infrastructure investments valued at £4.069m (incl vat) at Morriston Hospital. Works included installation of new electrical generator as resilience back-up for substation 4 which supplies acute areas such as critical care. These works were completed in 2019.  

This business case, Environmental Modernisation BJC2 Stage 2 (Phase 2), will provide a new Substation 6 that is fully compliant with Welsh Health Technical Memorandum/Health Technical Memorandum (WHTM/HTM) and British Standards. It will reduce the potential for Low Voltage (LV) overloading in Substations 3 & 4, which serve the highest clinical acuity areas of the site. In addition it will provide WHTM/ISO compliant ventilation infrastructure in Morriston’s Hospital Sterilisation and Decontamination Unit HSDU.  This is currently a significant risk for the Health Board with current ventilation in the area less than 50% the required levels.
Future phases will provide a whole-system infrastructure solution by addressing statutory and site strategy compliance requirements in Morriston’s Substations 3 & 4. This phase will provide additional electrical capacity to support known current and future clinical requirements within the main Morriston Hospital nucleus footprint for the next two to five years. 
Part A - The Strategic Context 
1.3 Business Strategies 
This BJC supports the following national, regional and local strategies plans and drivers for change and delivery of the main benefits: 
This investment supports WGov’s Decarbonisation Strategy and optimises links with SBUHBs wider renewable energy infrastructure solutions. 

It supports ‘A Healthier Wales’ (2018), the cluster approach to population health will underpin our plan to reconfigure the roles of our major hospitals and support the effective delivery of timely, high quality hospital based care when it is needed. 
This project aligns with key national, regional and local strategic drivers. Both SBU and Hywel Dda UHBs support this business case, which ‘fits’ with SBU HB’s Organisational Strategy: Better Health, Better Care, Better Lives 2019 - 2030, Clinical Services Plan 2019-2024, and our 3 year Recovery and Sustainability submitted in March 2022 and with the Masterplan for Morriston Hospital. 
This investment provides efficient infrastructure which supports: SBUHB's Decarbonisation Delivery Plan 2002-24’s objectives; SBUHBs emerging Estates Strategy, and; NHS Net Zero Wales’ improved energy performance target & a reduction in emissions target, which support  WHOs declaration of a global health (and climate) emergency (January 2020). 
It supports sustainability by providing an additional 6 Electrical Vehicle Charging (EVC) points, which support reduced carbon emissions, and; the new substation design solution optimises links with SBUHB’s new Solar Farm renewable energy infrastructure.

1.4 Key Interdependent Projects

The following projects are planned for the Morriston site over the next two to five years. Some, for example, The Hybrid Theatre and replacement/new diagnostic developments will be dependent on this investment and supports HV capacity in short term developments north of the main nucleus site:

Figure 1 – Interdependent Projects
[image: image3.png]Mid & West

Regional Hybrid Theatre
Pathology development
development

Diagnostic
equipment
projects - CT &
MRI





Part B - The Case for Change
1.5 Problems with Status Quo 

When Morriston’s existing Substations (3 & 4) were installed in the 1980s they were fully compliant with British Standards at that time. Now, both Substations 3 & 4 are in urgent need of investment due to the increased level of clinical acuity, which has intensified far beyond that originally envisioned. Increased levels of activity and acuity of services has placed immense strain on the existing electrical infrastructure. 

Morriston is an ‘Acute Hub’ under the key recommendations of the South Wales Programme and will require significant investment in its electrical resilience (i.e. duplication of essential capacities to provide back-up electrical supply in the event of a systems failure) in order to deliver clinical services in the future. Historically, the Health Board’s estate has been competing against other priorities for allocations for investment pressures on the capital programme. The resulting imbalance between demand for capital and the availability of capital has placed increased reliance on using robust risk methodology to identify areas of significant risk. Estates and Facilities Performance Management System (EFPMS) risk assessment methodology has provided a predictive model for capital investments, however, competition is increasing for scarce resources, and the aging profile of SBUHB’s acute sites and demand for more modern clinical services is placing severe pressure on the estate. This has contributed towards the funding ‘gap’ between what is desirable and what is achievable within current funding constraints and demand on services. 

This situation was recognised by the Welsh Government/NWSSP’s Major Risks Framework initiative, which addressed significant infrastructure risks across Wales, and with their assistance and the application of a robust risk methodology herein, SBUHB has identified and prioritised a number of significant and high risk areas for investment across our acute hospital estate, which are considered essential if current and future requirements are to be supported. 

The ventilation system at Morriston’s HSDU is non-compliant with ventilation rates - only 50% of required standards and pressure cascade non-compliant. Enhanced environmental air monitoring has been put in place to provide some assurance but this has also been failing recently requiring continual re-testing. This investment will address these issues and provide compliant infrastructure. 

1.6 Spend Objectives

In accordance with NHS Wales’s guidance and this infrastructure investment, the key spend objectives have been limited in scope as follows: 
Figure 2 – Spend Objectives
	Spend Objective 1
	Capacity - To free up capacity in two overloaded Substations (3 & 4) by providing additional capacity in a new Sub Station. Increase ventilation capacity in HSDU to compliant levels.

	Spend Objective 2
	Safety - To reduce risk and provide a safer working environment for staff. Reduce the risk of ineffective decontamination processes in HSDU.

	Spend Objective 3
	Efficiency & Effectiveness - To provide fully compliant electrical infrastructure facility and energy efficient ventilation plant in HSDU.


All the above to be achieved by end of the December 2023, subject to funding and planning approvals. There are no potential dis-benefits.  

1.7 Business Needs 

This investment will provide a new Substation fully compliant with WHTM/HTM and British Standards. 
This investment will reduce the potential for Low Voltage (LV) overloading in Substations 3 & 4, which serve the highest clinical acuity areas of the site. It will also provide WHTM/ISO compliant ventilation infrastructure in Morriston’s HSDU and provides a more resilient HSDU service for the Health Board’s three acute hospitals.
1.8 Potential Scope

This section describes the potential scope for the project in relation to the above business needs in terms of modalities and service drivers. The potential scope has been assessed against a continuum of need. The potential service scope framework options within these ranges are described in the figure below: 
Figure 3 - Potential Service Scope Framework Options
	Business as Usual
	Do Minimum
	Do Maximum

	Low Voltage (LV) insufficient capacity / poor safety / poor compliance in Morriston Hospital’s current Sub Stations 3 & 4. HSDU remains a significant Health Board risk.
	Provide additional HV/LV capacity to support Morriston Hospital’s electrical requirements within the main hospital nucleus over the next 2-5 years (supports known schemes on the main hospital site). Upgrade HSDU ventilation to WHTM/IOS compliant standards 
	Provide additional HV/LV capacity to support Morriston Hospital’s electrical requirements over the next 5-10 years (supports known schemes on the main hospital site) Upgrade HSDU ventilation to WHTM/IOS compliant standards


1.9 Main Outcomes and Benefits

The main potential outcomes benefits to patients, the Health Board and the wider health community would be classified in terms of cash releasing benefits (CRBs), non-cash releasing benefits (NCRBs), quantifiable or quantitative benefits (QBs), and non-quantifiable or qualitative benefits (NQBs). The main benefits include the following:
· Availability of modern Substation plant (NB Substation 6 is clinically compliant).
· Reduce risk of catastrophic failure in essential clinical systems.  
· Provide a safer working environment for estates staff.
· Provide spare LV/HV capacity for short-term development schemes in Substations 3 & 4.

· Provide compliant ventilation infrastructure in HSDU, replacing obsolete plant with modern equipment to achieve mandatory compliance requirements. 

· Improve patient safety and maintains a continuum of clinical services, having reduced overloading in Substations 3 & 4.
· Provide functionally safe and appropriate infrastructure to support clinical delivery.

· Provide improved control mechanisms. 
· Mitigate breakdown risk (direct & indirect) of essential plant and services impacting on patient services.
See Appendices C & D for further details.
1.10 Main Risks

The main business and service risks associated with the potential scope across all the options for this project together with their counter measures, are detailed in Appendix A. Refer to Appendix B for details of the appraisal team members. The key risks and mitigations are outlined below: 
	Risk
	Risk Rating
Probability x Impact
	Mitigation

	STRATEGIC RISKS:
	
	

	Programme delay due to WG approvals. Funding approval delayed or timing of funding does not match current programme. 
	3x3 = 9


	Regular liaison by SBUHB with WG with regards to development of BJC and timing of submission.

	Impact of labour market shortages, inflation on Plant and Materials
	5x4 = 20
	Ongoing monitoring of indices during FBC stage

	PLANNING RISKS:
	
	

	Content of Planning Conditions
	3x3 = 9
	Early review of requirements and programme for closure

	FINANCIAL RISKS:
	
	

	Capital costs - Capital Cost over-run 
	1x3 = 3
	BJC fully tendered, costs are scrutinised Liaison with WG SS

	Revenue affordability - Affordability of revenue model is over/under estimated
	1x3 = 3
	Finance Working Group established; Finance lead regularly report to Project Board.

	DESIGN RISKS:
	
	

	Planning guidance - Changes to Legislation/ British Standard/ HTM/ HBN/ ISO's/ CPA Accreditation/ HTA's/ Royal Colleges' guidance/ best practice
	2x4 = 8
	(1) Project Board monitors wider NHS design changes; (2) Continued liaison between partners

	Contaminated ground, both in the trenching areas external to the works area such as the adjacent field/substation area, road cross overs and cable trenching
	3x3 = 9
	Ground investigations

	Unforeseen service diversion works
	2x4 = 8
	Survey of all routes

	SITE & CONSTRUCTION RISKS:
	
	

	Validation of HSDU identifies issues delaying the department from reopening e.g., water quality tests, air tests
	3x3 = 9
	Protection of equipment, clean area regime, early testing to determine condition

	Logistics daily operation of hospital including deliveries
	3x3 = 9
	Liaison with Health Board

	Decommissioning and recommissioning of existing plant
	3x3 = 9
	Agree minimum requirement, record performance before decommissioning  and after recommissioning

	Vehicular/Pedestrian movements on site - proximity to public
	3x3 = 9
	Control of parking to minimise impact on access routes

	Contract works overlap with other projects on hospital site/impact of works on other hospital sites
	3x3 = 9
	SBUHB to advise of potential issue


1.11 Constraints and Dependencies
The key constraints are as follows:  
· Services must be maintained seamlessly during any works or systems replacements to avoid significant disruption of service delivery.

· Working within a live site. 

· Availability of capital funding and cash flow. 

· Deliver a cost effective and value for money solution.  

· Buildability of the technical solution, strategic ‘fit’ with the SDCP and planning permissions.
· The solution must be affordable in capital and revenue terms and be delivered within project budget.

· The solution must support WGov’s Decarbonisation Strategy by delivering additional electrical capacity and optimise links with SBUHBs wider renewable energy infrastructure solutions.

Recommendation

This BJC presents a compelling case for change given the significant risk to clinical services on the Morriston Hospital site of continued Low Voltage (LV) non-compliance and overloading risk is recommended that the Welsh Government support the investment proposals set out in this BJC.  It will provide WHTM/ISO compliant ventilation infrastructure in Morriston’s HSDU. 
This scheme can be undertaken as a single contract and building services could start October 2022, subject to funding approval.

	……………………………………………………...

Signed & Dated: 
	Deb Lewis, Deputy Chief Operating Officer, SBUHB


2 The Economic Case
2.1 Introduction

In accordance with the Capital Investment Manual and requirements of HMT’s The Green Book: Central Government Guidance on Appraisal and Evaluation (2018), this section of the business case demonstrates the wide range of options that have been considered in response to the potential scope identified in this BJC.   

2.2 Critical Success Factors

The Critical Success Factors (CSFs) have been identified to allow evaluation of the potential options. These are shown below:
Figure 4 – Critical Success Factors (CSFs)  
	CSF
	Description

	CSF1 Strategic Fit & Business Needs
	The solution must address the current and known future business needs of the main Morriston Hospital site for the next 2-5 years & improve staff safety.

	CSF2 Benefits Optimisation
	The solution should optimise benefits and provide value for money.

	CSF3 Potential Achievability
	The organisation’s ability to support clinical and non-clinical service delivery in the future & mitigate operational risk & reduce estate infrastructure risk profile.

	CSF4 Capacity and Reliability
	The ability to deliver the required services and deliverables – provide additional HV/LV capacity; Comply with British Standards and HTMs//WHTMs & Reduce overloading risk in Substations 3 & 4.

	CSF5 Potential Affordability
	The organisation’s ability to fund the required level of expenditure; viz, the capital and revenue consequences associated with the proposed investment.


2.3 Methodology 

The Appraisal Group identified a range of framework options (as follows) in accordance with Treasury Green Book and Capital Investment Manual. An Options Appraisal Workshop was held on in March 2021 A list of participants is attached in Appendix B. 
· Potential Service Scope Options – what is the potential coverage of the service to be delivered (the ‘what’);

· Potential Technical Solution Options – the potential technical (i.e. estates) options for delivering the preferred service solution option (the ‘where’);
· Potential Implementation Options – the potential timescales options for delivering the preferred service scope, preferred service solution, preferred technical solution options (the ‘when’);
· Potential Service Delivery Options – who will deliver the preferred service scope, preferred service solution, preferred technical solution, preferred implementation options (the ‘who’);
· Potential Finance Options – the potential funding and affordability options for delivering the preferred service scope, preferred service solution, preferred technical solution, preferred delivery options.
2.4 The Long Listed Framework Options 
The long list of options was generated using the Scoping Options framework. The sections below summarise the assessment of each scoping option as they were assessed against the Investment Objective and CSF criteria to determine their short list suitability. The framework options findings are summarised in Appendix C. The possible solutions were carried forward into the short list for further appraisal and evaluation. All the ‘discounted’ options were excluded at this stage. 
2.5 Summary of Short List Options

The short list is as follows: 
Figure 5 – Short List Options
	Option
	Reason for Acceptance or Rejection for further consideration

	Option 1 - Business as Usual (BAU) - Low Voltage (LV) insufficient capacity / poor safety / poor compliance in Morriston Hospital’s current Sub Stations 3 & 4 and HSDU remains a significant Health Board risk.
	Discounted – retained as baseline comparator.

	OPTION 2 - Do Minimum 
Provide additional HV/LV capacity to support Morriston Hospital’s main nucleus electrical requirements over the next 2-5 years; Develop fully compliant new Sub Station 6 & two Generators; It will provide WHTM/ISO compliant ventilation infrastructure in Morriston’s HSDU; Health Board delivery; Capital investment. 
	Shortlisted - supports known schemes on the main hospital site. Provides essential additional HV/LV capacity to support Morriston Hospital’s main nucleus and reduces risk a catastrophic failure on substations 3 & 4. Mitigates immediate Health Board decontamination compliance risk within HSDU. Supports HV capacity in short term developments north of the main nucleus site.

	OPTION 3 - Do Maximum 

Provide additional HV/LV capacity to support Morriston Hospital’s electrical requirements over the next 5-10 years; Develop fully compliant existing sub stations 3 & 4 and provide new Sub Station 6 & two Generators; It will provide WHTM/ISO compliant ventilation infrastructure in Morriston’s HSDU; Health Board delivery; Capital investment.
	Rejected - supports known schemes on the main hospital site. Higher strategic planning risk. Supports HV/LV capacity in short term developments north of the main nucleus site. Significantly more capital investment required compared to Do Minimum.


2.6 Indicative Capital and Revenue Costs of each Short Listed Option

Capital Costs
The project’s cost advisor, Gleeds, has prepared fully tendered capital costs. The capital costs excluding VAT and Optimism Bias (see Appendices D & E) are as follows:

Figure 6 – Capital Costs (excl VAT £000s and including Optimism Bias above baseline)
	
	Option 2

Do Minimum

	Works Cost
	11,341

	Fees
	1,300

	Non Works Costs
	556

	Equipment Costs
	10

	Planning Contingency
	660

	Anticipated inflationary increases
	134

	Total
	14,001

	OB Adjustment (works only)
	227

	Grand Total
	14,228


The key assumptions underlying the development of the capital costs are:

· Capital Cost includes works, non-works, abnormals allowances, equipment costs and risk contingency, which is assessed at 5%. 
· Given the volatility of current market conditions, as affected by the Ukraine war, high and rising energy costs and other supply chain issues, and in line with current experience elsewhere within Wales, we allowed for recovery of ‘abnormal’ inflation over and above levels of inflation known and anticipated
. Should abnormal inflation occur, then Kier will be entitled to a Compensation Event for same. The sum included in our cost forms includes an anticipated allowance which has been informed by our independent Cost Advisor. 
· The BISPUB SEC indices at this stage is 285 for 2Q 2022. The Business Case reporting Index will be the standard one for Wales of 0.97.
· This BJC excludes a Generic Economic Analysis (GEM) as agreed with WGov given this project has limited options.
· Please see Appendix G for the Whole Life Costing Report. 
· VAT is excluded in this section of the case.
Revenue Costs

The future revenue cost for the preferred option above baseline are outlined in the figure below:  
Figure 7 – Revenue cost impact above baseline (£000’s)
	
	Option 2
Do Minimum 

	Non-recurring Revenue 2022/23
	106

	Recurring Revenue from 2023/24
	16


The revenue costings have been costed at 2022/23 prices. The additional service revenue costs will be covered within the Health Board’s financial plan
2.7 The Preferred Option
The preferred option is Option 2 – Do Minimum (i.e. Provide additional LV capacity to support Morriston Hospital’s electrical requirements over the next 2-5 years; Develop fully compliant new Sub Station 6 & two Generators; Health Board delivery; Capital investment). 

The Substation would comprise of a new building constructed of brickwork to meet planning requirements. The Substation building would have an Aluminium standing seam roof and profiled aluminium soffit and fascias. The Substation would be situated within a compound surrounded by new palisade type fencing measuring 2.3 metres in height. The Substation building would house Switchgear and Transformer units. Two Standby Generators are proposed within the compound to provide compliant emergency power under an “N + 1” arrangement to achieve WHTM standard.
The LV Switchroom would comprise of a new building constructed of brickwork to match that in the existing vicinity. The LV Switchroom would also have an Aluminium standing seam roof and profiled aluminium soffit and fascias. The LV Switchroom would house 2 main LV Switch panels.

A new oil line would be installed to form a connection between the new Substation and Morriston Hospital’s oil storage tanks. Site Location and scheme drawings are included in Appendix G. 

The development would also involve the following works:

· Permanent SuDS Drainage Pond and SuDS Swale to serve the proposed Substation;

· Hardstanding Footpaths to the west, south and east of the Substation; 

· Enhancement of the access located off Mynydd Gelli Wastad Road and the construction of a hardstanding turning area using asphalt, and; 

· Installation of 6 permanent parking spaces with electric vehicle charging points for the Health Board’s service vehicle fleet to contribute to their carbon reduction programme.

The preferred option also includes the replacement of the air handling plant and associated ventilation system modifications supplying the HSDU at Morriston hospital. The equipment is currently obsolete resulting in significant ventilation capacity issues for the decontamination area. Therefore, considerable non-compliance is evident resulting in high decontamination risks for the Health Board.
3 The Commercial Case
3.1 Introduction

This section of the BJC outlines the proposed ‘deal’ as outlined in the Economic Case. The BJC is seeking to secure public funding from the WGov’s ‘All Wales Capital Programme’. 
3.2 Required Services

Provision of a new Substation 6 in accordance with HSE requirements. Building Standards, HTM/WHTN and Statutory compliance requirements and technical commissioning.  Provide WHTM/ISO complaint ventilation infrastructure in Morriston’s HSDU.
3.3 Key Appointments & Contract Arrangements
The following key appointments will be made via WGov’s Building for Wales Framework procurement route to ensure delivery of this project: 
· Supply Chain Partner (construction and design team services) - Kier Western
· Health Board Project Manager (HBPM)
Health Board Cost Advisor (HBCA) (through the Building for Wales framework procurement route) and Supervisor (through an OJEU approved framework). Other technical services are to be being provided by the Health Board.
The contract is the NEC Engineering and Construction Contract (April 2013) with main option clause C (target cost). The Pain/Gain principle will apply.
3.4 Required Facilities and Compliance
The new substation and HSDU ventilation system will be in compliance with associated Health Technical Memorandum/Welsh Health Technical Memorandums (HTM/WHTM). 
3.5 Potential for Risk Management

A risk register has been compiled and costed relative to risks that apply over the whole of the project lifecycle at this stage (see Appendix A). The planning contingency has been assessed by an independent cost advisor. The planning contingency includes non-recoverable VAT and excludes OB. This assessment of risk and complies with NHS Wales Shared Services Partnership – Specialist Estates Services (NWSSP - SES) guidance at this planning stage.

3.6 Agreed Charging Mechanisms

A collaborative working model is to be adopted. All charging mechanisms will be covered within the framework agreement. Under this arrangement Kier Construction Ltd have been selected by the Health Board from the NHS Building for Wales Regional Framework.   

Gleeds, the Health Board’s appointed Cost Advisor, confirms the scheme will be tendered to a minimum of 80% cost certainty in accordance with the Framework requirements. 

The Contractor will invoice SBUHB Health Board in accordance with the Payment Mechanism.  The agreed Payment Mechanism is 4 weekly assessments by the Health Board Cost Advisor with payment due within 14 days of the Assessment Date.
3.7 Agreed Contact Length

The contract will cover approx. 55 weeks. 
3.8 Personnel Implications (including TUPE)

TUPE (Transfer of Undertaking and Protection of Employee) will not apply to this investment.
3.9 FRS5 - Accountancy Treatment

It is assumed that public funding will be allocated for this project and therefore capital will be included on the balance sheet.
3.10 Indicative Timescales

The indicative milestones are set out below (see Appendix H):
Figure 8 – Key indicative milestones
	Activity
	Due Date

	Health Board approved BJC
	July 2022

	WGov approves BJC
	Sept 2022

	Mobilise and commence works
	October 2022

	Completed (subject to contractor’s programme)
	October 2023

	Commissioning 
	November 2023

	HSDU & new Substation fully operational
	December 2023

	Technical Project Evaluation (approx. 3 months post new build handover)
	March 2024

	Benefits Realisation (12 months post operational)
	December 2024


4 Funding and Affordability
4.1 Introduction

The purpose of this section is to set out the indicative financial implications of the proposed investment (as set out in the Economic Case) and proposed Deal (as described in the Commercial Case).  

4.2   Capital

The fully tendered capital cost assessment were undertaken by Gleeds, Cost Advisors. These are as follows (see Appendices D & E): 
Figure 9 – Capital Costs (incl recoverable VAT £000s and excl Optimism Bias above baseline)
	
	Option 2

Do Minimum

	Works Cost
	13,609

	Fees
	1,560

	Non Works Costs
	667

	Equipment Costs
	12

	Planning Contingency
	792

	Anticipated inflationary increases
	161

	Less Recoverable VAT
	-268

	Total
	16,533


The key assumptions underlying the development of the capital costs are:
· Capital Cost includes works, non-works, abnormals allowances, equipment costs and risk contingency, which is assessed at 5%. 

· Given the volatility of current market conditions, as affected by the Ukraine war, high and rising energy costs and other supply chain issues, and in line with current experience elsewhere within Wales, we allowed for recovery of ‘abnormal’ inflation over and above levels of inflation known and anticipated
. Should abnormal inflation occur, then Kier will be entitled to a Compensation Event for same. The sum included in our cost forms includes an anticipated allowance which has been informed by our independent Cost Advisor. 

· The BISPUB SEC indices at this stage is 285 for 2Q 2022. The Business Case reporting Index will be the standard one for Wales of 0.97. 

· This BJC excludes a Generic Economic Analysis (GEM) as agreed with WGov given this project has limited options.
· Please see Appendix G for the Whole Life Costing Report. 

· VAT is at 20% except for the professional fee and other vat recoverable elements (please see Appendix O)

Figure 10 – Capital Expenditure £000’s (incl of non-recoverable VAT & excl Optimism Bias)

	£(000’s)
	Prior Years
	2022/23
	2023/24
	2024/25
	Total

	Capital Costs
	887
	5,339
	10,289
	18
	16,533

	Capital Funding
	917
	5,309
	10,289
	18
	16,533


4.3 Impact on the Balance Sheet and Impairment

Figure 11 – Revenue Expenditure £000’s above baseline (£000s)
	£(000’s)
	22/23
	23/24
	24/25
	25/26
	26/27
	27/28

	Depreciation
	
	81
	325
	325
	325
	325

	Impairment (AME) Initial Valuation
	
	10,078
	
	
	
	


The Health Board will engage the services of the District Valuer to provide a valuation of the scheme following completion. This scheme would result in an estimated AME Impairment of £10,078k on the initial valuation of the unit and this will need to be taken through the Health Board’s SOCNE in 2023/24. The Health Board would require funding from WGov and this will be included in the AME impairment funding submission to WGov in 2022/23. 

The Health Board will require additional recurring depreciation of £325k from 2024/25 with one quarter depreciation required in 2023/24 of £81k.
4.4 Income and Expenditure Analysis
The future revenue cost for the preferred option above baseline are outlined in the figure below:  
Figure 12 – Revenue cost impact above baseline (£000’s)
	
	Option 2
Do Minimum 

	Non-recurring Revenue 2022/23
	106

	Recurring Revenue from 2023/24
	16


The revenue costings have been costed at 2022/23 prices. The additional service revenue costs will be covered within the Health Board’s financial plan
4.5 Overall Affordability

The project requests capital investment ‘not to exceed’ £16.533m (including VAT and excl Optimism Bias) to be allocated by the WGov.  

The Health Board requests AME Impairment funding of £10,078k in 2023/24 and funding to support recurrent depreciation costs of £325k from 2024/25.
5 The Management Case
5.1 Introduction

The section of the BJC addresses the achievability of the project. 
5.2 Project Management Arrangements

To ensure successful project delivery a robust project management reporting structure has been established.  The structure is based on the Prince2 principles, with key members of the project team trained in Prince2 methodology. 
The Health Board’s experience of developing and delivering complex projects in a Prince2 environment ensures diligent management and thorough clinical involvement throughout all parts of the development:
Programme:
· The Senior Responsible Owner (SRO) is Mrs Sian Harrop-Griffiths, Head of Strategy, SBUHB. 
· The Programme Director is Mr Simon Davies, Assistant Director of Strategy, SBUHB. 

Project: 

· The Senior Responsible Owner (SRO) is Mrs Deb Lewis, Deputy Chief Operating Officer, SBUHB. 
· The Project Director, is Mr Mark Gapper, Head of Engineering, SBUHB who has the authority and responsibility to manage delivery of the project on behalf of the key stakeholders. The Project Director reports via the Project Board to the Project SRO.
· The Project Manager, is Mr Scott Matthews (Mace) who will support the Project Director.
Programme Management Structure

The reporting structure is shown below:

Figure 13 – Environment Modernisation Programme Management Structure
[image: image4.png]Programme Reporting Structure:

Senior Responsible Owner
Sian Harrop-Griffiths, Director of Strategy

Programme Director
Simon Davies, Asst. Director of Strategy (Capital)

Project Director
Mark Gapper, Head of Engineering

Health Board Project Manager Project User
Cost Advisor Groups

Constructor, M&E & Design Team

Reporting structure < >





Project Management Structure

A summary project management structure diagram is shown below for the Morriston Hospital site: 

Figure 14 – Morriston Hospital’s Project Management Structure
[image: image5.png]Insert  Design

View  Q Tell me what you want to do.

1~ Terms of Morriston (2) - PowerPaint

Heather Edwards (Swansea Bay UHB - Capital Planing)

Morriston Infrastructure Modernisation Phase 2 Stage 2 vfinal(3) [Compatibiity Mode] - Word

ﬁ & cut

ER) Copy - o
< Format Panter | sjige EjSection =

Clipboard r. Sides

(=) Do

] Reset

Slide 2 of 3

I -

0z
Type here to search

&

0
N=lela] a3

ALLD OG-,
%N L} s Arene
Paragrapn Draving
DR T R TR R RIS R AR XY RXRE RARE RS R
=y

Morriston EIP Ph2 - Reporting structure

Senior Responsible Owner

Deputy Chief Operating Officer, SBUHB

l

Project

Head of Engineering

Director

Project Support Groups:

Service Delivery Management

Fa

ies Management

Estates Capital & Operational
Management

Health & Safety, Manual
Handling & Fire

Health Board SBUHB Project Health Board Cost
Project Manager Liaison Manager Advisor
L
Mace Capital Planning Gleeds
:
' v '

Infection Control

Supply Chain Partner &
Integrated Design Team

Kier Construction Ltd

Project User Group.

IM&T

Formal Reporing >
Smcturs

i —
S >

Classification - Public

Procurement

Notes

W Comments | [E]

2 share Tell me what you want to do
ﬁ vl -0 -]& & 2 T AaBb asBbccdi AaBbCc
Pt ormatpainter | B 1 U 7ok X X0 A = Gi- | appendi  Bullet!  Caption
~ Cipboara 5 Font 5
o) 2 L s

flsme
P Find -
AaBbCcD AaBbCcDi AaBbCcDi AaBbCcDi AaBbCt AaBbCcD AaBbCcDi AaBbCel 111111 1 AaB AaBbCcD AaBbCeDi | 4y Replace
Figuiel € normall  nomal2  subbullet TSubSect.. TSubSubS.. Table cont.. ToblePa.. Legalleve. Section  Quote  cvlistpan. = g
stes 5 Editing ~

Figure 14 — Morriston Hospital’s Project Management Structure

bk 5.3 Use of Special Advisers

For Terms of Reference please see Appendix I.

Special Advisors will be appointed in accordance with the Treasury Guidance: Use of Special Advisers.

Figure 15 — Special Advisors

] Role

Advisor

VAT Advisor

Ernst & Young

] 5.4 Arrangements for Benefits Realisation

A project level Benefits Plan and detailed Benefits Realisation Register specifically addressing technical,

decarbonisation and net zero targets are included in Appendices J & K. Benefits realisation will be

monitored at Programme Board.

N 5.5 Building Design Strategy and Decarbonisation

] The Design Team have devised a building design and services’ strategy that includes solutions in support
= i of NHS Wales Net Zero targets and in accordance with the requirements of the NHS Decarbonisation
=R Strategic Delivery Plan (March 2021) as appropriate to the design and the scale of this development.

[ Page200f37 6ds0words [

The new plant is designed to modern standards and the development will provide six Electrical Vehicle




For Terms of Reference please see Appendix I. 

5.3 Project Bank Account

The project is aiming to establish a Project Bank Account to support the implementation of WGov’s policy. At this stage there are on-going discussions being held at on all-Wales basis with WGov around known issues with the ability of the Supply Chain Partner (Kier Western) to currently support a Project Bank Account. If these issues are resolved, the Project Bank Account can hopefully be established during the period of WGov scrutiny.
5.4 Use of Special Advisers
Special Advisors will be appointed in accordance with the Treasury Guidance:  Use of Special Advisers.
Figure 15 – Special Advisors
	Role
	Advisor

	VAT Advisor
	Ernst & Young


5.5 Arrangements for Benefits Realisation

A project level Benefits Plan and detailed Benefits Realisation Register specifically addressing technical, decarbonisation and net zero targets are included in Appendices J & K. Benefits realisation will be monitored at Programme Board.
5.6 Building Design Strategy and Decarbonisation
The Design Team have devised a building design and services’ strategy that includes solutions in support of NHS Wales Net Zero targets and in accordance with the requirements of the NHS Decarbonisation Strategic Delivery Plan (March 2021) as appropriate to the design and the scale of this development.  The new plant is designed to modern standards and the development will provide six Electrical Vehicle Charging (EVC) points. 
5.7 Community Benefits

Community Benefits will be agreed at contract stage with the main contractor.  

5.8 Audit & Assurance

In accordance with the NHS Wales Infrastructure Investment Guidance (2018), the Health Board has sought input from NWSSP Audit and Assurance Services (Specialist Services Unit - NWSSP: A&A (SSu) to “assess the risk profile of the scheme and provide appropriate levels of review”, as required, noting that a Programme level implementation plan was proposed at PBC stage. A fully resourced and costed audit plan has provisionally been developed and provision included within this case (Appendix L). 

5.9 AEDET (Achieving Excellence Design Evaluation Toolkit) & BREEAM
It has been confirmed with NWSSP that an AEDET and BREEAM will not be required for this scheme as it does not involve any direct patient or clinical staffing contact.
5.10 Arrangements for Risk Management 

A risk framework has been established which outlines the process for managing risk associated with developing this project, including a structure for identifying and mitigating operational and construction related risks. The risk register would use qualitative and quantitative measures to calculate the overall level of risk according to likelihood of any risk occurrence multiplied by the potential impact. The Project Board will formally review the risk register at key stages of the project. A project risk register is attached at Appendix A.
5.11 Planning Permissions 

Planning permissions (ref. 2021/2621/FUL) were approved by Local Planners on the 14th March 2022.
5.12 Post Evaluation Arrangements / Lessons Learned
Post Evaluation and lessons learned will be undertaken as appropriate to this investment and in accordance with best practice and NHS guidance. 
5.13 NHS Wales Gateway Review (Stage 3 – Investment Decision) 
A Risk Potential Assessments (RPA) has been carried out for this project. A copy is included in Appendix M.  A Gateway review could be arranged WGov would carry out post submission of this BJC in accordance with WGov Investment Guidance. Further Gateways would be completed according to Office of Government Commerce (OGC) guidelines following further evaluation. 
5.14   Contingency Plans

The Health Board can identify two major category of project failure: failure to achieve business case approval to deliver the project; failure of the main contractor to deliver the new sub-station to time. 

The contingency plan for the project in the event of failure to achieve business case approval is for the Health Board to continue to revise its plans, working with WGov to develop an alternative solution that is acceptable. 
In the event of Supply Chain failure, SB UHB would seek recompense in line with the agreed contractual arrangements and other contractor to complete the project. 
Appendix A – Risk Register
Appendix B – Project Board Membership
Appendix C – Framework Option Appraisal

Appendix D – Cost Form
Appendix E – Optimism Bias Mitigation
Appendix F – Whole Life Costing 
Appendix G – Drawings
1:00 elevations (1)
1:00 elevations (2)
1:00 elevations (3)
Site Plan (1)
Site Plan (2)
Site Location Plan
Appendix H – Management Control Plan
Appendix I – Terms of Reference
Appendix J – Benefits Realisation Plan 

Appendix K – Benefits Realisation Register
Appendix L - Audit & Assurance Plan

Appendix M – Gateway Review - (RPA) 
Appendix O – VAT Letter
Abbreviations

	(W)HBN
	Welsh Health Building Note

	(W)HTM
	Welsh Health Technical Memorandum

	AEDET
	Achieving Excellence Design Evaluation Toolkit

	AHP
	Allied Health Professional

	AME
	Annually Managed Expenditure

	ARCH
	A Regional Collaboration for Health

	BAU
	Business as Usual

	BIS PUBSEC
	Business Innovation and Skills (Firm Price Index) Tender Price Index of Public Sector Building Non-Housing

	BJC
	Strategic Outline Business Case

	BREEAM
	Building Research Establishment Environmental Assessment

	BRP
	Benefits Realisation Plan

	CRBs
	Cash Releasing Benefits

	CRUK
	The Cancer Research UK’s

	CSF
	Critical Success Factor

	CSP
	(SB UHB’s) Clinical Service Plan

	CSS
	Clinical Support Services

	CT
	Computed Tomography

	CVU HB
	Cardiff and Vale University Health Board

	DCC
	Direct Clinical Care

	DECAG
	Departmental Cost Allowance Guide 

	DGH
	District General Hospital

	DGM
	Divisional General Manager

	DoH 
	Department of Health

	ECAG
	Equipment Cost Allowance Guide

	EQA
	External Quality Assessment

	FBC
	Full Business Case

	GEM
	Generic Economic Model

	HB
	Health Board

	HBCA
	Health Board Cost Adviser

	HBPM
	Health Board Project Manager

	HCSE
	Health Care Systems Engineering

	HDU
	High Dependency Unit

	HIA
	Health Impact Assessment

	HMt
	Her Majesty’s Treasury

	HSA
	Health and Safety Executive

	HV
	High Voltage

	ICU
	Intensive Care Unit

	TP
	Integrated Medium Term Plan

	LV
	Low Voltage

	MDT
	Multi-Disciplinary Team

	NCRBs
	Non Cash Releasing Benefits

	NEC
	New Engineering Contract

	NICE
	The National Institute for Health and Care Excellence

	NWSSP SES
	NHS Wales Shared Services Partnership – Specialist Estates Services

	OBC
	Outline Business Case

	OCP
	Organisational Change Policy

	OGC
	Office of Government Commerce

	OOHs
	Out of Hours

	PDP
	Portfolio Delivery Plan (ARCH)

	PEP
	Project Execution Plan

	PET
	Positron Emission Tomography

	PIA
	Privacy Impact Assessment

	PPE
	Post Project Evaluation

	QA
	Quality Assurance

	RIBA
	Royal Institute of British Architects

	RPA
	Risk Potential Assessment

	RTT
	Right to Treatment

	SB UHB
	Swansea Bay University Health Board

	SBU HB
	Swansea Bay University Health Board

	SDCP
	Site Development Control Plan

	SOP
	Standard Operating Procedure

	TAT
	Turn Around Time

	VATS
	Video-assisted thoracoscopic surgery

	VfM
	Value for Money

	WAST
	Welsh Ambulance Service NHS Trust

	WGov
	Welsh Government

	WHSSC
	Welsh Health Specialised Services Committee

	WTE
	Whole Time Equivalent

	HSDU
	Hospital Sterilisation and Decontamination Unit

	EVC
	Electrical Vehicle Charging

	EFPMS
	Estates and Facilities Performance Management System


[image: image6.png]


[image: image7.png]



Business Justification Case (BJC)





Morriston Infrastructure Modernisation 


Phase 2 Stage 2








� In the event of further abnormal inflation that is the direct cause of a further significant increase in costs, then the ‘Welsh Procurement Policy Note WPPN 09/21: Sourcing building materials for construction projects in Wales’ document will take effect. In the event that Policy Document WPPN  09/21 takes effect, and the SCP can demonstrate that additional unforeseeable inflation costs have been incurred as a consequence of said event, then contract clause 60.1 (14) shall apply.


� In the event of further abnormal inflation that is the direct cause of a further significant increase in costs, then the ‘Welsh Procurement Policy Note WPPN 09/21: Sourcing building materials for construction projects in Wales’ document will take effect. In the event that Policy Document WPPN  09/21 takes effect, and the SCP can demonstrate that additional unforeseeable inflation costs have been incurred as a consequence of said event, then contract clause 60.1 (14) shall apply.





1
17

