## Version
Ref | Comments | Author | Date
[enter the next number in the sequence] | [Enter a description here of the changes made to this version] | [Enter the initial of the person making the changes | [Enter the date when the changes were made]
v1 | Draft
v2 | Updated by Comments
v3 | Updated by Comments
v4 | Updated by Comments
v5
v6
v7
v8
v9
v10
v11
v12
v13
v14
v15
v16
v17

## Risk Register Template
Lead organisation
Project:
Project Risk Register
Identification |  |  |  | Assessment |  |  |  |  | Quantification |  | Management |  |  |  | Risk Quantification Calculation
Nr | Risk Description | Risk Consequence: 1. Time 2. Cost 3. Quality 4. Operational | Scheme | Probability | Impact | Score | Risk Allocation | Category | Quantified Unquantified | Estimated cost impact £ | Management Actions | Action Owner | Review Date | Comments | Cost if it happens £ | Likelihood Factor | Expected Value | Basis
1 | STRATEGIC / PLANNING / FINANCIAL
1.1 | Design brief | Time, Cost, Quality, Operational |  |  |  | 0 |  | Planning | Unquantified |  |  | Client |  |  |  | 0.25 | 0
1.2 | Ineffective project management arrangements during project planning and delivery stages | Time, Operational |  |  |  | 0 |  | Planning | Unquantified |  |  | Client |  |  |  | 0.1 | 0
1.3 | Internal approvals delayed | Time |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.25 | 0
1.4 | Capital funding approval delayed or timing of funding does not match our current programme | Time |  |  |  | 0 |  | Financial | Unquantified |  |  | Client |  |  |  | 0.25 | 0
1.5 | Capital costs - Capital cost over-run | Time, Cost, Quality |  |  |  | 0 |  | Financial | Unquantified |  |  | Client |  |  |  | 0.25 | 0
1.6 | Revenue affordability - Affordability of revenue model is over/under estimated | Quality, Operational |  |  |  | 0 |  | Financial | Unquantified |  |  | Client |  |  |  | 0.1 | 0
2 | DESIGN/CDM/REGULATIONS
2.1 | Siting and adequacy of Contractors Compound and Site Set-Up | Time, Cost, Quality |  |  |  | 0 |  | Financial | Unquantified |  |  | TRJ |  |  |  | 0.25 | 0
2.2 | Suitable Contractor Emergency Procedures | Quality, Operational |  |  |  | 0 |  | Operational | Unquantified |  |  | TRJ |  |  |  | 0.05 | 0
2.3 | Unforeseen service diversion works | Time, Cost, Quality, Operational |  |  |  | 0 |  | Operational | Unquantified |  |  | Client |  |  |  | 0.5 | 0
2.4 | Encountering unforeseen services. | Time, Cost, Quality |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
2.5 | Fire strategy and detection during the works | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.25 | 0
2.6 | Asbestos in existing buildings; only to older part | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Asbestos to be delt with outside the Risk register |  | 0.5 | 0
2.7 | Contaminated Waste - Other | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
2.8 | Vehicular/Pedestrian movements on site - proximity to public | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | TRJ |  |  |  | 0.5 | 0
2.9 | Extent and scope of the design to be frozen for construction phase | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
2.1 | Impact of non agreed derogrations or design assumption | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
2.11 | Current as built drawings do not reflect current installation | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.75 | 0
2.12 | Changes to design requirements | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.75 | 0
3 | M&E SPECIFIC RISK
3.1 | Proposed design may not be suitable and/or may require further unanticipated approvals | Time, Cost, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
3.2 | Plant Room Space for services coordination | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
3.3 | Specialist equipment to be clearly defined | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
3.4 | Temporary works | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
3.5 | Maintenance legacy items | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Within Tender |  | 0.25 | 0
4 | PRE-CONSTRUCTION PHASE
4.1 | Inflation/Market Price Increases | Time, Cost, Quality, Operational |  |  |  | 0 |  | Financial | Unquantified |  |  | Client |  |  |  | 0.25 | 0
4.2 | Isolations by maintenance not being able to be carried out | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.25 | 0
4.3 | Critical services being affected by the works, isolation and diversion time scales affecting the programme of works; complex critical path | Time, Cost, Quality, Operational |  |  |  | 0 |  | Operational | Unquantified |  |  | Client |  | Health Board risk |  | 0.75 | 0
4.4 | Working within live environment | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
4.5 | Maintaining existing fire escape routes | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
4.6 | Working within existing department | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
4.7 | Logistics construction work inc decant requirements | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
4.8 | Logistics of supporting daily activities inc deliveries | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
4.9 | Shut downs | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
4.1 | Operational continuity during works | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
4.11 | Approval timings | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
4.12 | General disruption due to construction activity | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
5 | CONSTRUCTION PHASE
5.1 | Noise/Dust/Vibration Risk; to units around the works areas | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | TRJ |  |  |  | 0.5 | 0
5.2 | Access/Egress; especially on walk ways in roof space | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | TRJ |  |  |  | 0.5 | 0
5.3 | Security of site compound and unfixed materials | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | TRJ |  | Manage out |  | 0.5 | 0
5.4 | Below ground drainage | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client/TRJ |  |  |  | 0.5 | 0
5.5 | Roof design; unforeseen issues once roof is stripped | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client/TRJ |  |  |  | 0.5 | 0
5.6 | Fire Stopping generally; but fire stopping above existing walls etc | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client/TRJ |  |  |  | 0.5 | 0
5.7 | Screed levels; during demolition and unforeseen floor level differences | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client/TRJ |  |  |  | 0.5 | 0
5.8 | Changes to the planned Phasing causing operation of the site changes and ways of working; additional Out Of Hours Working | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
5.9 | Uncharted services | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
5.1 | Operational policy changes | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
5.11 | Decommisioning and recommisioning of existing plant | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
5.12 | Protection of existing permanent works/making good | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
5.13 | Site working hours; COVID | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
5.14 | Working within live environment | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Unquantified |  |  | Client |  |  |  | 0.5 | 0
5.15 | Risk of accidental removal/Isolation of current systems; Hospital service interuption | Time, Cost, Quality, Operational |  |  |  | 0 |  | Strategic | Quantified |  |  | Client |  | Delt with direct by Health Board |  | 0.5 | 0
5.16 | Construction noise, adjacent buildings: general acoustics | Time, Cost, Operational |  |  |  | 0 |  | Operational | Quantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
5.17 | Existing roof condition | Time, Cost, Operational |  |  |  | 0 |  | Operational | Quantified |  |  | Client |  | Health Board risk |  | 0.75 | 0
5.18 | Aceess and egress from existing roof; court yard; General Contractor access | Time, Cost, Operational |  |  |  | 0 |  | Operational | Quantified |  |  | Client |  | Health Board risk |  | 0.75 | 0
5.19 | Potential for specialist building fabric requirements requiring specialist design advice | Time, Cost, Operational |  |  |  | 0 |  | Operational | Quantified |  |  | Client |  | Health Board risk |  | 0.75 | 0
5.2 | Material sign off and availability | Time, Cost, Operational |  |  |  | 0 |  | Operational | Quantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
5.21 | Planning permission and any requirements; Any Building Control (Building Safety Act) or Net Zero Standard requirements | Time, Cost, Operational |  |  |  | 0 |  | Operational | Quantified |  |  | Client |  | Health Board risk |  | 0.5 | 0
58
[6 empty] | 0 |  |  | Total £: | 0 | [5 empty] | Contingency Total £: | 0
[16 empty] | QRA Results: | 0
[10 empty] | 0 | [5 empty] | % of contingency | #DIV/0!
Total of above £
[10 empty] | 0 | [6 empty] | 0
[10 empty] | 0 |  |  |  |  | #REF! |  | 0
0
2472672.1819
2472672.1819
Current FBC Inclusion £
Variance Schedule to FBC £

## Risk Matrix
Probability | Almost certain 90% | 5 | 5 | 10 | 15 | 20 | 25
| Likely 75% | 4 | 4 | 8 | 12 | 16 | 20
| Possible 50% | 3 | 3 | 6 | 9 | 12 | 15
| Unlikely 25% | 2 | 2 | 4 | 6 | 8 | 10
| Rare 5% | 1 | 1 | 2 | 3 | 4 | 5
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Insiginificant | Minor | Moderate | Major | Catastrophic
Impact
To close a risk, enter 0 into Probability and Impact
[6 empty] | 1 | Green
2
3
4
5
6
7
8
[6 empty] | 9 | Amber
10
11
12
13
14
15
[6 empty] | 16 | Red
17
18
19
20
21
22
23
24
25